## Hoja1
Main Tasks | 2020 |  |  |  | 2021 |  |  |  | 2022 |  |  |  | 2023 |  |  |  | 2024 |  |  |  | 2025 |  |  |  | 2026 |  |  |  | 2027
| Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2
Signage of R/D | bar: 2020 Q4
Reinforcement CONQUITO
All activities needed to begin reinforcement construction | bar: 2021 Q4 to 2022 Q4
Reinforcement Construction | bar: 2022 Q4 to 2023 Q2
A. Establishment of Quito Innovation Center
A-1 Remodeling of the innovation center (including design and construction) | bar: 2022 Q4 to 2026 Q1
A-2 Establishment and equipment of the Innovation Center | bar: 2024 Q1 to 2025 Q3
B. Establishment of the Operation Plan of Quito Innovation Center
Coordination with pmc and diagnostics | bar: 2022 Q1 to 2023 Q1
B-1 Design of the Business model and portfolio of services for the Center | bar: 2022 Q4 to 2024 Q2
B-2 Design and implement a capacity building program for the Innovation Center | bar: 2023 Q1 to 2027 Q2
C. Public Innovation Lab design and Business Model
C-1Design of the Public Innovation Lab management model | bar: 2023 Q1 to 2024 Q1
C-2 Consultancy for an operation of Public Innovation Lab | bar: 2023 Q4 to 2024 Q3
D. Design and implementation of Productive Clusters
D-1 Analyze the local economy for the cluster implementation | bar: 2022 Q3 to 2024 Q2
D-2 Develop the operational model for the cluster set-up | bar: 2024 Q3 to 2025 Q3
D-3 Policy Consultancy based on 4th economic revolution for the operation of the cluster | bar: 2025 Q2 to 2026 Q2
3. Project Management
Monitoring and Evaluation | bar: 2021 Q1; 2022 Q1; 2023 Q1; 2024 Q1; 2025 Q1; 2026 Q1; 2027 Q2